Here's a step-by-step guide for PGRs on how to construct a Gantt chart to help you visualise and plan your research timeline effectively.

## Gantt Chart Guide for PGRs

A Gantt chart is a visual project management tool that helps you plan, schedule, and track tasks over time. For PGRs, it’s especially useful for organising research milestones, data collection, writing, and submission deadlines.

### Step 1: Define Your PhD Phases

Break your PhD journey into major phases. These typically include:

- Literature Review

- Research Design

- Data Collection

- Data Analysis

- Writing Chapters or papers if you are doing your PhD by publication

- Revision & Editing

- Submission & Viva Preparation

### Step 2: Break Down Each Phase into Tasks

Each phase should be broken into specific tasks. For example:

#### Literature Review

- Identify key databases (Oct–Nov 2025)

- Read 50 core papers (Nov 2025–Jan 2026)

- Annotate and summarise findings (Dec 2025–Feb 2026)

#### Data Collection

- Ethics approval (May 2026)

- Pilot study (June 2026)

- Full data collection (July–Sept 2026)

Step 3: Choose a Tool to Create the Gantt Chart

You can use:

- Excel or Google Sheets (manual but flexible)

- Microsoft or Trello (visual and collaborative)

- Notion (great for integrating notes and tasks)

- GanttProject (free desktop tools)

- Online tools like TeamGantt

### Step 4: Assign Timeframes

Estimate how long each task will take. Be realistic and include buffer time of 20%.

Give a start and end data for each task

Tip: Use academic calendars to avoid planning major tasks during holidays or busy teaching periods.

### Step 5: Add Milestones and deliverables

Milestones are key achievements or deadlines. Examples:

- Submit project plan: Jan 2026

- Finish APR report: May 2026

- IPAP: June 2026

- Literature review chapter draft: April 2026

### Step 6: Visualize Dependencies

Some tasks depend on others. For example:

- You can’t start data analysis until data collection is complete, or you might need ethics approval first.

- Writing results depends on analysis.

### Example Gantt Chart plan see attached excel file with example plan

### Final Tips

- Review monthly: Update your chart as your project evolves.

- Include teaching, conferences, and publications.

- Colour-code tasks by type (e.g., writing, data, admin).

- Share with your supervisor for feedback and accountability

- Build up gradually but always start with what you know for year one.