Liverpool Biochemistry Centenary Meeting

Programme Committee Meeting 13 December 2000

Present:	Prof. Huw Rees (chair), Dr Andy Bates, Dr Dave Fernig, Dr Sandy McLennan, Dr Mike White

1.	Apologies were received from Prof. Philip Rudland.

2.	Minutes  This meeting was intended as an opportunity to catch up with the current state of play.  No minutes were considered.

3.	Budget  It was confirmed that initial approaches for sponsorship had been successful, and the current list consisted of:

Biochemical Society	£5000 + secretarial support

Cancer and Polio Research Fund	£10000

Astra Zeneca	£5000

Society for Endocrinology	up to £3000	colloquium costs – Nuclear receptors

CCID		colloquium costs – Host-pathogen

Total

In addition is was agreed that the following organisations and companies should be approached:

Action

The Wellcome Trust	DGF/PSR

EU	DGF/PSR

Ares Serona (Switzerland)	DGF/PSR

Glaxo – SK	PSR

Pfizer	HHR

Astra	MRHW

Zeiss	MRHW

Promega	MRHW

Thermoquest	DGF

Invitrogen	ADB

Micromass	HHR

Applied Biosystems	ADB

Incyte	AGM

Oxford Biomedica	MRHW

MerseyBIO	DGF/PSR/JMC

4.	Colloquia  All the colloquia organisers have produced tentative lists of speakers.  In addition, Phill Hawkins has proposed some additional Pleanary speakers.  The list of Plenaries is almost finalised (see below) and it was agreed that HHR/ADB would clarify this situation with Phill Hawkins.

It was considered important that we co-ordinate the number of speakers in each colloquium (5 per half-colloquium), so the timings of the parallel sessions are in phase, and that we be kept fully informed by organisers of developments.  The following timetable was suggested:

Early January	After clarification of the situation with Phill Hawkins, colloquium organisers will be asked to informally invite their preferred speakers during January.

March 1	Meeting to review finances

March	Put accepted plenaries on Web, plus any other speaker acceptances.

March 31	Official invitations from The Biochemical Society

September 4	Final funding review

5.	Plenaries  Of the eight proposed plenary speakers, seven have accepted our invitation.  Only Susan Lindquist has not replied.  It was agreed that in the first instance, she should be approached again, but that other speakers such as those suggested by Phill Hawkins should be considered subsequently (but see current discussion: 9/1/01).

6.	Historical Lecturer  It was agreed to approach George Pitt in the first instance, but that George Britton and/or Rob Beynon be considered as alternatives.

7.	Social Events  DGF suggested that he will mail the various options for social events and venues to the Programme Committee in early January.  The importance of booking appropriate venues early was emphasised.

7.	AOB  It was agreed that a final decision about the viability of the meeting, in relation to a detailed budget and known sources of sponsorship and income be made one year in advance of the meeting, namely 4/9/01.

Andy Bates

9/1/01